## Release 3
SL No | Task Name | Task Type | Status | Comments
1 | All the report items should be properly aligned | UI | Completed | Changes in all the financial pages
2 | Dashboard\Employee, show only active employee count | UI | Completed | Changes in home.jsp and homecontroller
3 | Dashboard\Bills, show only pending bills count | UI | Completed | Changes in home controller and billsDAO,billsDO, billsService
4 | Dashboard\Project, show only active projects count | UI | Completed | Changes in home and homecontroller
5 | Dashboard\Invoice, show only pending invoice count | UI | Completed | Changes in home controller and invoiceDAO, invoiceService
6 | Dashboard\Expenses, show Total amount | UI | Completed | Changes in home and homecontroller
7 | Dashboard\Customers, show list of Customers | UI | Completed | Changes in home.jsp and homecontroller
8 | Dashboard\Vendors, show list of Vendors | UI | Completed | Changes in home and homecontroller
9 | Report button will be replace with pdf icon | UI | Completed | Changes in all report pages and image added in icons folder
10 | Show animated info icon if any bills pending and about to pay with in 5 days | UI | Completed | Changes in home.jsp and image added into icons folder
11 | Add payroll in dashboard | UI |  | Added
12 | Send asset type id instead of asset id to retrieve asset report | Backend | Completed | Changes done in AssetReportServlet page
13 | Money value should be shown with comma | UI | Completed | Changes in jsp pages and CommonUtil
14 | CTC should show complete name | UI | Completed | Changes in EmpCTC Controller
15 | CTC enddate not updated properly | Backend | Completed | Changes in EmpCTC Controller
16 | If CTC updated, send mail to employee | Backend | Completed | New pages added CTCEmailServlet, CTCEmailProxyUtil, CTC_Email_template and changes in empctc.jsp
17 | In Bills report total no of bills should show | UI | Completed | Changes in BillsReportServlet
18 | For different users some fields not working | UI | Completed | Changes in Controllers and WebManager.java
19 | Scrollbar In every page should not be there | UI | Completed | Changes in appstyle.css
20 | Dashboard/Payroll show total amount for current financial year | UI | Completed | Chnages in HomeController and home.jsp
21 | Show particular modules for particular user in dashboard | UI | Completed | Changes in home.jsp
22 | Send pdf when employees ctc updated | Backend | Completed | Changes in empctc and new servlet page added
23 | Show pdf icon for Empctc details after updating their ctc | Backend | Completed | Changs in empctc and new servlet page
24 | Deducting TDS in payroll according to their Annual CTC | Backend & UI | Completed | Chnages in Payroll jsp
25 | Bonus Column should add in payroll and should show in payslip if bonus present | Backend & UI | Completed | Changes in PayrollDO, jsp and Util
26 | Edit Access to HRUser also | UI | Completed | Changes in viewemployee.jsp
27 | Experience input field change to year and month | UI | Completed | Changes in viewemployee.jsp & addemployee.jsp
28 | Update not working for middle name and languages known in employee | UI | Completed | Changes in viewemployee.jsp
29 | view employee arrow images and showing same tab when again come to that page | UI | Completed | Changes in viewemployee.jsp